# SAP IS-Retail (SAP S/4HANA Retail) Implementation Plan

Business requirements and processes, design, configuration, chart of accounts, integration, finance worked example, testing, Azure ETL data migration, cutover, go-live, hypercare and production

Isaac Detch – SAP Project Management Consultant (FICO)

Version 1.0 – October 2026

Table of Contents

# 1. Executive Summary

[CLIENT] Retail operates 50 stores, one distribution center and an online shop on a mix of legacy merchandising, POS back-office and finance systems. Prices and promotions are maintained in several places, store replenishment is largely manual, POS sales reach finance two to three days late, and vendor rebates are tracked in spreadsheets.

This plan implements SAP IS-Retail – delivered in S/4HANA as SAP S/4HANA Retail for merchandise management – as the single system for merchandise master data, buying, pricing and promotions, replenishment and allocation, store and DC inventory, POS sales integration, vendor rebates and finance. The plan covers every phase from business requirements to hypercare and steady-state production operations.

## 1.1 Objectives and success measures

| Objective | Measure | Target |
| --- | --- | --- |
| Single source of article, price and promotion data | Price discrepancies at POS | < 0.1% of scanned items |
| Automated store replenishment | Share of store orders generated automatically | ≥ 85% |
| Daily store P&L | POS sales posted to G/L | By 06:00 the next day |
| Inventory accuracy | Store stock accuracy (cycle counts) | ≥ 97% |
| Vendor rebate capture | Rebates accrued vs. contractually due | 100% accrued monthly |
| Faster close | Month-end close | WD+4 |

## 1.2 Scope

| In scope | Out of scope (phase 2) |
| --- | --- |
| Merchandise category hierarchy, articles (generic & variants), sites, vendors | Fashion season & collection management (SAP S/4HANA for fashion) |
| Assortments, listing, sales price calculation, promotions | Customer loyalty and CRM |
| Purchasing, replenishment, allocation, stock transport orders | Unified demand forecasting & markdown optimisation |
| DC operations in EWM; store goods receipt, transfers and counts (Fiori) | Franchise and wholesale |
| POS outbound and inbound via CAR / POS DTA; sales audit | Store labour scheduling |
| Vendor rebates (condition contracts, Settlement Management) |  |
| Finance: AP, AR, cash & card settlement, inventory valuation, store P&L, financial statements |  |

## 1.3 Document structure

| Chapter | Content |
| --- | --- |
| 2 | Business requirements |
| 3 | Business processes and process flows |
| 4 | Solution architecture and design |
| 5 | Chart of accounts and account determination |
| 6 | Configuration |
| 7 | Integration |
| 8 | Finance integration and worked example to the financial statements |
| 9 | Testing |
| 10 | Data migration – Azure ETL to SAP Migration Cockpit staging tables |
| 11 | Cutover |
| 12 | Go-live, hypercare and production operations |
| 13 | Project plan, governance and risks |
| 14 | Glossary of abbreviations and terms |
| App. A | Transaction code index |

# 2. Business Requirements

Figure 2-1. Requirement areas and their dependencies – every area ends in finance

## 2.1 Master data and merchandise structure

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| BR-MD-01 | Four-level merchandise category hierarchy (division, department, merchandise category, article). | Must | Every article assigned to one merchandise category (MC); reports roll up by hierarchy. |
| BR-MD-02 | Fashion basics are maintained as generic articles with colour and size variants; each variant has its own EAN/UPC. | Must | Generic article TS-100 creates 3+ variants with EANs. |
| BR-MD-03 | Store, DC and online sites share a template (site profile) and are created in under 30 minutes. | Should | New site created by copy with listing and supply source. |
| BR-MD-04 | Vendors maintained as Business Partners with EDI settings and purchasing conditions. | Must | Vendor BP with purchasing org R100, info records, EDI partner profile. |

## 2.2 Assortment, pricing and promotions

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| BR-PR-01 | Articles are listed to stores by assortment (store cluster). | Must | Article sellable only in stores where listed. |
| BR-PR-02 | Retail prices are calculated from cost with margin targets and price-point rounding (e.g. .99). | Must | VKP5 proposes price; price points applied. |
| BR-PR-03 | Promotions with temporary prices by store group and date range are sent to POS automatically. | Must | Promo price active at POS on start date, removed after end date. |
| BR-PR-04 | Price changes reach all POS terminals before store opening. | Must | POS outbound complete by 05:00. |

## 2.3 Buying, replenishment and allocation

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| BR-BY-01 | DC replenishment from forecast with vendor lead times; POs sent by EDI. | Must | Replenishment run creates POs; EDI ORDERS transmitted. |
| BR-BY-02 | Store replenishment from DC based on POS consumption (min/max or forecast). | Must | Daily STOs DC01 → stores created automatically. |
| BR-BY-03 | New-season and promotional merchandise allocated to stores by allocation rules. | Should | Allocation table generates STOs / POs by store quantity. |
| BR-BY-04 | Vendor rebates accrued on every invoice and settled per contract. | Must | Condition contract accruals posted; settlement credit to vendor. |

## 2.4 DC and store operations

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| BR-OP-01 | DC inbound, putaway, picking and shipping run in EWM with RF devices. | Must | Inbound delivery → GR → putaway; outbound pick → GI. |
| BR-OP-02 | Stores receive DC deliveries on mobile Fiori apps by scanning. | Must | Store GR updates store stock same day. |
| BR-OP-03 | Stores perform cycle counts and annual inventory; differences post to shrinkage. | Must | Count approved; difference to 52300000 by store. |
| BR-OP-04 | Store-to-store transfers are possible. | Should | Transfer posted with in-transit stock. |

## 2.5 Point of sale and omnichannel

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| BR-POS-01 | POS sales, returns and tenders from all stores reach S/4HANA daily, audited. | Must | CAR sales audit approves; IDocs processed without errors by 06:00. |
| BR-POS-02 | POS sales reduce store stock and post revenue, tax, cost of sales and tenders. | Must | Postings as in §8.1. |
| BR-POS-03 | Online orders are fulfilled from the DC or ship-from-store with real-time stock. | Should | Stock availability API returns site stock. |

## 2.6 Finance and reporting

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| BR-FI-01 | Inventory valued at moving average cost by site; profit center per store and DC. | Must | Store P&L and inventory by profit center. |
| BR-FI-02 | Cash deposits and card settlements are reconciled automatically by store. | Must | Bank statement auto-match ≥ 95%. |
| BR-FI-03 | Gross margin by store, MC and article available daily. | Must | Margin Analysis and CAR reports. |
| BR-FI-04 | Shrinkage reported by store and MC. | Must | Inventory differences by profit center and MC. |

## 2.7 Non-functional requirements

| ID | Requirement |
| --- | --- |
| NFR-01 | POS inbound: 50 stores × [TICKETS_PER_DAY] tickets/day processed within the 01:00–05:00 window. |
| NFR-02 | Replenishment run for 50 stores × [ACTIVE_ARTICLES] articles completes in < 60 minutes. |
| NFR-03 | Store apps available 07:00–23:00 local time; 99.5% availability. |
| NFR-04 | Segregation of duties between price maintenance, vendor master, PO approval and payment. |
| NFR-05 | PCI DSS: no card numbers stored in S/4HANA or CAR; tokenised tenders only. |

# 3. Business Processes

## 3.1 Process hierarchy

| L1 | L2 | L3 processes |
| --- | --- | --- |
| Merchandise management | Master data | MC hierarchy, article (generic/variant), site, vendor, EAN, characteristics |
|  | Assortment & listing | Assortment creation, store clustering, listing/de-listing |
|  | Pricing & promotions | Sales price calculation, price changes, promotion planning, POS download |
| Buy & move | Procure to DC | Replenishment, PO, EDI, ASN, GR, invoice, rebate accrual, payment |
|  | Replenish store | Store replenishment, allocation, STO, DC pick/ship, store GR |
|  | Inventory | Transfers, counts, adjustments, returns to vendor |
| Sell | Store sales | POS checkout, returns, end-of-day, sales audit, POS inbound |
|  | Online sales | Order capture, availability, fulfilment, returns |
| Finance | Record to report | Cash & card reconciliation, rebates settlement, valuation, store P&L, close, statements |

The three core end-to-end flows are shown below as swimlanes (who does what, in which system).

## 3.2 Procure to distribution center

Figure 3-1. Procure to DC: master data, replenishment, EDI, goods receipt, invoice, rebate accrual, payment

## 3.3 Replenish store from DC

Figure 3-2. Store replenishment and stock transport from DC01 to store ST01

## 3.4 Point of sale to ledger

Figure 3-3. POS transactions through CAR sales audit to S/4HANA and finance

## 3.5 Pricing and promotions

Figure 3-4. From purchase price to POS price

## 3.6 Vendor rebates

Figure 3-5. Condition contract accrual and settlement

# 4. Solution Architecture and Design

## 4.1 Solution landscape

Figure 4-1. IS-Retail solution landscape

| Tier | S/4HANA Retail | CAR / POS DTA | EWM |
| --- | --- | --- | --- |
| DEV | [S4D] / 100 | [CARD] | embedded / [EWMD] |
| QA | [S4Q] / 200 | [CARQ] | [EWMQ] |
| PRE-PROD | [S4R] / 300 | [CARR] | [EWMR] |
| PROD | [S4P] / 400 | [CARP] | [EWMP] |

## 4.2 Organisational structure

Figure 4-2. Retail organisational structure

| Object | Value | Design note |
| --- | --- | --- |
| Company code | US10 | Legal entity; YCOA; USD |
| Purchasing organisation | R100 | Central buying for all sites |
| Distribution chains | R100/10 stores · R100/20 online | Prices and assortments maintained per distribution chain |
| Sites | DC01 (DC), ST01–ST50 (stores), WEB1 (online) | Each site is a plant + customer; valuation at site level |
| Profit centers | 1100 DC, 2101–2150 stores, 3100 online | Store P&L and balance sheet by document splitting |
| Storage locations | DC01: 0001 (EWM-managed); stores: 0001 sales floor, 0002 back room | Store stock simple, no WM in stores |

## 4.3 Merchandise category hierarchy and articles

Figure 4-3. Merchandise category hierarchy and generic article

| Design element | Decision |
| --- | --- |
| Article categories | 00 single article, 01 generic article (with 02 variants), 11 prepack, 10 sales set |
| Article types | HAWA trading goods for merchandise; NLAG non-stock for store supplies; display and prepack types as required [VERIFY] |
| Variant-creating characteristics | COLOR, SIZE assigned to merchandise categories via class type 026 |
| EAN/UPC | Main EAN per variant and unit of measure; additional EANs allowed |
| Article numbering | Generic: external (TS-100); variants: generic + suffix (TS-100-BLK-M) |
| Inventory management | Article-based at site, valuated at moving average price [DECISION: retail method for stores?] |

## 4.4 Key design decisions

| ID | Decision | Rationale |
| --- | --- | --- |
| DD-01 | Inventory valuation at moving average cost per site (not retail method) | Accurate COGS by store; simpler with S/4HANA; markdowns do not revalue stock |
| DD-02 | POS integration via CAR / POS DTA with sales audit; aggregated IDocs to S/4 | Volume reduction; audit before posting |
| DD-03 | DC on EWM; stores on Fiori store apps without warehouse management | Right-sized complexity |
| DD-04 | Vendor rebates in condition contracts (Settlement Management) | Replaces legacy subsequent settlement; accruals per invoice |
| DD-05 | One profit center per store | Store P&L and balance sheet |
| DD-06 | Store replenishment from DC only; direct-store-delivery for selected vendors [DECISION] | Supply chain control |

# 5. Chart of Accounts

Company code US10 uses one operational chart of accounts based on the SAP Best Practices chart YCOA (8-digit accounts), extended with retail-specific accounts: POS tender clearing (cash, card, gift card, online payment provider), vendor rebate receivables and income from condition contracts, gift-card and store-credit liabilities, refund liability for expected returns, POS discounts, shrinkage, vendor markdown funding, store occupancy and card fees, and a data migration clearing account (39990000) that must be zero after the initial stock and G/L balance loads. The machine-readable source is finance/chart_of_accounts.csv (114 accounts).

## 5.1 Design principles

- YCOA as the base, so SAP Best Practices content (account determination, financial statement version, reports) works with minimal change; retail accounts are added in free number ranges. Account numbers in this document are the client’s design – verify them against the YCOA delivered in your release before build [VERIFY].

- Inventory at moving average cost per site; one inventory account (13400000) for all merchandise, split by site and profit center through the material ledger and document splitting.

- Every POS tender has its own clearing account that must be zero once the bank deposit or acquirer settlement is matched – the daily control for 50 stores.

- Vendor rebates and vendor-funded markdowns reduce cost of goods sold (52500000, 52600000), not revenue.

- Returns and discounts are revenue deductions (41100000–41300000) so gross and net sales can be reported by store.

- Profit center per store and DC (2101–2150, 1100) with document splitting gives a store P&L and balance sheet.

- Migration clearing 39990000: initial stock (movement 561) and G/L balances are both posted against it; it must net to zero (reconciled automatically by the ETL).

## 5.2 Account groups

| Group | Content | Number of accounts |
| --- | --- | --- |
| CASH | Cash, bank and POS tender clearing | 8 |
| RECV | Receivables, vendor rebates, prepaid, tax | 7 |
| INV | Merchandise inventory | 4 |
| FIXA | Fixed assets, right-of-use, intangibles, deferred tax | 17 |
| PAYB | Payables, GR/IR, accruals, gift cards, refund liability, taxes | 16 |
| DEBT | Leases and borrowings | 4 |
| EQTY | Equity | 2 |
| MIGR | Data migration clearing | 1 |
| REVN | Revenue and sales deductions | 9 |
| COGS | Cost of goods sold, shrinkage, rebates | 10 |
| PERS | Personnel | 4 |
| OCCU | Store occupancy | 5 |
| SGA | Selling, general and administrative | 12 |
| DEPR | Depreciation and amortisation | 5 |
| FIN | Financial result | 4 |
| TAX | Income taxes | 2 |
| SECC | Secondary cost elements (CO only) | 4 |

## 5.3 Assets (1xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 11001000 | Bank 1 – Main Account | 1.1.1 | Cash and cash equivalents | House bank (FI12) | Balance sheet |
| 11001010 | Bank 1 – Incoming Payments Clearing | 1.1.1 | Cash and cash equivalents | Bank statement posting rules (OT83) | Balance sheet |
| 11001020 | Bank 1 – Outgoing Payments Clearing | 1.1.1 | Cash and cash equivalents | Payment program (F110) | Balance sheet |
| 11009400 | Store Cash in Transit | 1.1.1 | Cash and cash equivalents | POS inbound tender mapping (cash) | Balance sheet |
| 11009500 | Payment Card Clearing (acquirer) | 1.1.1 | Cash and cash equivalents | POS inbound tender mapping (card) | Balance sheet |
| 11009600 | Online Payment Service Provider Clearing | 1.1.1 | Cash and cash equivalents | Commerce / PSP settlement | Balance sheet |
| 11009700 | Gift Card Redemption Clearing | 1.1.1 | Cash and cash equivalents | POS inbound tender mapping (gift card) | Balance sheet |
| 11009800 | Store Change Funds & Petty Cash | 1.1.1 | Cash and cash equivalents | Cash journal (FBCJ) | Balance sheet |
| 12100000 | Trade Receivables – Domestic (B2B / franchise) | 1.1.2 | Trade receivables | Customer reconciliation account | Balance sheet |
| 12190000 | Allowance for Doubtful Receivables | 1.1.2 | Trade receivables | Manual / valuation | Balance sheet |
| 12600100 | Vendor Rebate Receivable (condition contract accruals) | 1.1.4 | Vendor receivables and rebates | Settlement Management accrual account | Balance sheet |
| 12600200 | Vendor Receivables – Returns to Vendor & Debit Memos | 1.1.4 | Vendor receivables and rebates | MIRO subsequent debit / RTV | Balance sheet |
| 12600300 | Vendor Down Payments | 1.1.4 | Vendor receivables and rebates | Special G/L A (OBYR) | Balance sheet |
| 13400000 | Inventory – Merchandise (trading goods) | 1.1.5 | Inventories | OBYC BSX (valuation class 3100) | Balance sheet |
| 13400100 | Inventory – Stock in Transit (cross-company STO) | 1.1.5 | Inventories | OBYC BSX / UMB | Balance sheet |
| 13400300 | Inventory – Store Supplies & Packaging | 1.1.5 | Inventories | OBYC BSX (valuation class 3050) | Balance sheet |
| 13400900 | Inventory Valuation Adjustment (LCM / NRV) | 1.1.5 | Inventories | Manual / valuation run | Balance sheet |
| 14000000 | Prepaid Expenses (rent deposits, insurance) | 1.1.3 | Other current assets | Manual | Balance sheet |
| 14100000 | Sales & Use Tax Receivable | 1.1.3 | Other current assets | Tax codes (FTXP) | Balance sheet |
| 16100000 | Land | 1.2.1 | Property & equipment | AA account determination (AO90) | Balance sheet |
| 16200000 | Buildings (owned DC) | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 16300000 | Leasehold Improvements (store fit-out) | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 16400000 | Store Fixtures & Equipment | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 16500000 | POS Hardware & IT Equipment | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 16600000 | DC Material Handling Equipment | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 16700000 | Assets under Construction (new stores & remodels) | 1.2.1 | Property & equipment | AO90 (AuC settlement) | Balance sheet |
| 16800000 | Right-of-Use Assets – Store & DC Leases | 1.2.2 | Right-of-use assets | Lease accounting (RE-FX / LAE) | Balance sheet |
| 16900000 | Software & Intangible Assets | 1.2.3 | Intangible assets | AO90 | Balance sheet |
| 17200000 | Accumulated Depreciation – Buildings | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 17300000 | Accumulated Depreciation – Leasehold Improvements | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 17400000 | Accumulated Depreciation – Store Fixtures | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 17500000 | Accumulated Depreciation – POS & IT | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 17600000 | Accumulated Depreciation – DC Equipment | 1.2.1 | Property & equipment | AO90 | Balance sheet |
| 17800000 | Accumulated Amortisation – Right-of-Use Assets | 1.2.2 | Right-of-use assets | Lease accounting | Balance sheet |
| 17900000 | Accumulated Amortisation – Software | 1.2.3 | Intangible assets | AO90 | Balance sheet |
| 18000000 | Deferred Tax Assets | 1.2.4 | Deferred tax assets | Manual | Balance sheet |

## 5.4 Liabilities (2xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 21100000 | Trade Payables – Domestic | 2.1.1 | Trade payables | Vendor reconciliation account | Balance sheet |
| 21100100 | Trade Payables – Foreign (import) | 2.1.1 | Trade payables | Vendor reconciliation account | Balance sheet |
| 21150000 | Payables – Landlords | 2.1.1 | Trade payables | Vendor reconciliation account | Balance sheet |
| 21200000 | GR/IR Clearing – Merchandise | 2.1.2 | GR/IR clearing | OBYC WRX | Balance sheet |
| 21200100 | GR/IR Clearing – Freight & Duties | 2.1.2 | GR/IR clearing | OBYC FR1 / FR3 | Balance sheet |
| 21300000 | Accrued Expenses | 2.1.3 | Accrued and payroll liabilities | Accrual Engine / manual | Balance sheet |
| 21400000 | Payroll Clearing | 2.1.3 | Accrued and payroll liabilities | Payroll posting | Balance sheet |
| 21410000 | Payroll Withholdings & Benefits Payable | 2.1.3 | Accrued and payroll liabilities | Payroll posting | Balance sheet |
| 21500000 | Gift Card Liability (unredeemed) | 2.1.4 | Gift card and customer liabilities | POS inbound (gift card sale) | Balance sheet |
| 21510000 | Customer Deposits & Layaway | 2.1.4 | Gift card and customer liabilities | POS inbound / special G/L | Balance sheet |
| 21520000 | Store Credit & Customer Credit Memos | 2.1.4 | Gift card and customer liabilities | POS inbound | Balance sheet |
| 21530000 | Refund Liability – Expected Returns | 2.1.5 | Refund liabilities | Period-end estimate | Balance sheet |
| 21540000 | Right-to-Recover Returned Goods (contra) | 2.1.5 | Refund liabilities | Period-end estimate | Balance sheet |
| 22000000 | Sales Tax Payable | 2.1.7 | Taxes payable | Tax code MWS / jurisdiction codes | Balance sheet |
| 22100000 | Use Tax Payable | 2.1.7 | Taxes payable | Tax codes | Balance sheet |
| 22200000 | Income Tax Payable | 2.1.7 | Taxes payable | Manual | Balance sheet |
| 23000000 | Lease Liabilities – Current | 2.1.6 | Lease liabilities – current | Lease accounting | Balance sheet |
| 23100000 | Lease Liabilities – Non-current | 2.2.1 | Lease liabilities – non-current | Lease accounting | Balance sheet |
| 23200000 | Revolving Credit Facility & Bank Loans | 2.2.2 | Borrowings | Treasury / manual | Balance sheet |
| 24000000 | Deferred Tax Liabilities | 2.2.3 | Deferred tax liabilities | Manual | Balance sheet |

## 5.5 Equity and migration clearing (3xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 31000000 | Share Capital | 3.1 | Share capital | — | Balance sheet |
| 32000000 | Retained Earnings | 3.2 | Retained earnings | OB53 (balance carry-forward) | Balance sheet |
| 39990000 | Data Migration Clearing (must be zero after go-live) | 3.9 | Migration clearing | OBYC GBB-BSA (mvt 561) / G/L balance load offset | Balance sheet |

## 5.6 Revenue and sales deductions (4xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 41000000 | Revenue – Merchandise Sales (stores) | 4.1.1 | Gross sales | VKOA ERL (POS sales) | Primary – revenue (11) |
| 41000100 | Revenue – Online Sales | 4.1.1 | Gross sales | VKOA ERL | Primary – revenue (11) |
| 41000200 | Revenue – Wholesale & Franchise | 4.1.1 | Gross sales | VKOA ERL | Primary – revenue (11) |
| 41100000 | Sales Returns (contra revenue) | 4.1.2 | Returns and discounts | POS inbound returns (mvt 252) | Primary – sales deduction (12) |
| 41200000 | POS Discounts & Coupons | 4.1.2 | Returns and discounts | POS inbound (discount condition) | Primary – sales deduction (12) |
| 41300000 | Employee Discounts | 4.1.2 | Returns and discounts | POS inbound (discount condition) | Primary – sales deduction (12) |
| 41500000 | Gift Card Breakage Revenue | 4.1.3 | Other revenue | Period-end estimate | Primary – revenue (11) |
| 41600000 | Delivery & Service Fee Revenue (online) | 4.1.3 | Other revenue | VKOA ERL | Primary – revenue (11) |
| 41700000 | Other Operating Income (vendor marketing funds) | 4.1.3 | Other revenue | Settlement Management | Primary – revenue (11) |

## 5.7 Cost of goods sold (5xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 50000000 | COGS – Merchandise (stores) | 5.1.1 | Cost of goods sold | OBYC GBB-VAX (mvt 251) | Primary cost (1) |
| 50000100 | COGS – Merchandise (online) | 5.1.1 | Cost of goods sold | OBYC GBB-VAX | Primary cost (1) |
| 50100000 | Inbound Freight & Duties (not capitalised) | 5.1.2 | Freight and duties | OBYC FRL / manual | Primary cost (1) |
| 50200000 | Price Differences – Merchandise | 5.1.3 | Price differences | OBYC PRD | Primary cost (1) |
| 52300000 | Inventory Differences / Shrinkage | 5.1.4 | Shrinkage rebates and markdowns | OBYC GBB-INV (mvt 701/702) | Primary cost (1) |
| 52400000 | Damaged & Scrapped Merchandise | 5.1.4 | Shrinkage rebates and markdowns | OBYC GBB-VNG (mvt 551) | Primary cost (1) |
| 52500000 | Vendor Rebate Income (COGS reduction) | 5.1.4 | Shrinkage rebates and markdowns | Settlement Management (condition contract) | Primary cost (1) |
| 52600000 | Vendor Promotion & Markdown Funding (COGS reduction) | 5.1.4 | Shrinkage rebates and markdowns | Settlement Management | Primary cost (1) |
| 52700000 | Inventory Write-down to NRV | 5.1.4 | Shrinkage rebates and markdowns | Manual / valuation run | Primary cost (1) |
| 52800000 | Cash Discounts Received | 5.1.4 | Shrinkage rebates and markdowns | OBXU SKE | Primary cost (1) |

## 5.8 Operating expenses (6xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 61000000 | Salaries & Wages – Stores | 6.1 | Personnel expenses | Payroll posting | Primary cost (1) |
| 61000100 | Salaries & Wages – DC | 6.1 | Personnel expenses | Payroll posting | Primary cost (1) |
| 61000200 | Salaries & Wages – Head Office | 6.1 | Personnel expenses | Payroll posting | Primary cost (1) |
| 61100000 | Payroll Taxes & Benefits | 6.1 | Personnel expenses | Payroll posting | Primary cost (1) |
| 62000000 | Rent & Occupancy – Stores (variable & short-term) | 6.2 | Occupancy expenses | FB60 / RE-FX | Primary cost (1) |
| 62100000 | Common Area Maintenance | 6.2 | Occupancy expenses | FB60 | Primary cost (1) |
| 62200000 | Utilities | 6.2 | Occupancy expenses | FB60 | Primary cost (1) |
| 62300000 | Store Maintenance & Repairs | 6.2 | Occupancy expenses | FB60 / PM order | Primary cost (1) |
| 62400000 | Security & Loss Prevention | 6.2 | Occupancy expenses | FB60 | Primary cost (1) |
| 63000000 | Advertising & Marketing | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 63100000 | Store Supplies & Shopping Bags | 6.3 | Selling general and administrative | OBYC GBB-VBR (cost center) | Primary cost (1) |
| 63200000 | Outbound Freight & E-commerce Fulfilment | 6.3 | Selling general and administrative | Shipment cost settlement | Primary cost (1) |
| 63300000 | IT & Software Subscriptions | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 63400000 | Communication | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 63500000 | Insurance | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 63600000 | Bank & Payment Card Fees | 6.3 | Selling general and administrative | Bank statement posting rules (acquirer fee) | Primary cost (1) |
| 63700000 | Cash Handling (armoured car) | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 63800000 | Professional Fees | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 63900000 | Travel | 6.3 | Selling general and administrative | FB60 | Primary cost (1) |
| 64000000 | Depreciation – Leasehold Improvements & Fixtures | 6.4 | Depreciation and amortisation | AO90 / AFAB | Primary cost (1) |
| 64100000 | Depreciation – POS & IT | 6.4 | Depreciation and amortisation | AO90 / AFAB | Primary cost (1) |
| 64200000 | Depreciation – DC Equipment & Buildings | 6.4 | Depreciation and amortisation | AO90 / AFAB | Primary cost (1) |
| 64300000 | Lease Cost / ROU Amortisation | 6.4 | Depreciation and amortisation | Lease accounting | Primary cost (1) |
| 64400000 | Amortisation – Software | 6.4 | Depreciation and amortisation | AO90 / AFAB | Primary cost (1) |
| 65000000 | Store Pre-opening Costs | 6.3 | Selling general and administrative | Project settlement | Primary cost (1) |
| 65100000 | Gain / Loss on Disposal of Assets | 6.3 | Selling general and administrative | AO90 | Primary cost (1) |

## 5.9 Financial result (7xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 70000000 | Interest Income | 7.1 | Financial result | Manual / treasury | P&L (not CO-relevant) |
| 70100000 | Interest Expense | 7.1 | Financial result | Manual / treasury | P&L (not CO-relevant) |
| 70200000 | Interest on Lease Liabilities | 7.1 | Financial result | Lease accounting | P&L (not CO-relevant) |
| 70300000 | Exchange Rate Differences (import purchases) | 7.1 | Financial result | OBA1 KDF / KDB | P&L (not CO-relevant) |
| 79000000 | Income Tax Expense – Current | 8.1 | Income taxes | Manual | P&L (not CO-relevant) |
| 79100000 | Income Tax Expense – Deferred | 8.1 | Income taxes | Manual | P&L (not CO-relevant) |

## 5.11 Secondary cost elements (CO) (9xxxxxxx)

| Account | Description | FSV node | Statement line | Account determination | CO |
| --- | --- | --- | --- | --- | --- |
| 94000000 | Assessment – DC Costs to Stores | 9.0 | — (secondary; nets to zero) | Assessment cycle (KSU1) | Secondary – assessment (42) |
| 94100000 | Assessment – Head Office Costs to Stores | 9.0 | — (secondary; nets to zero) | Assessment cycle (KSU1) | Secondary – assessment (42) |
| 94200000 | Activity Allocation – DC Handling (cases picked) | 9.0 | — (secondary; nets to zero) | Activity type CASE (KP26) | Secondary – activity allocation (43) |
| 96000000 | Settlement – Store Opening & Remodel Projects | 9.0 | — (secondary; nets to zero) | Settlement profile (WBS → AuC) | Secondary – internal settlement (21) |

## 5.12 Automatic account determination

| Area | Key | Business event | Debit | Credit |
| --- | --- | --- | --- | --- |
| MM (OBYC) | BSX | Inventory posting – all merchandise movements (valuation class 3100) | 13400000 | 13400000 |
| MM (OBYC) | WRX | GR/IR clearing – vendor goods receipt vs invoice | 21200000 | 21200000 |
| MM (OBYC) | PRD | Price differences when stock is insufficient to absorb invoice variance | 50200000 | 50200000 |
| MM (OBYC) | GBB-VAX | POS sale / delivery goods issue (mvt 251 / 601) – cost of goods sold | 50000000 |  |
| MM (OBYC) | GBB-INV | Physical inventory differences (mvt 701 / 702) | 52300000 | 52300000 |
| MM (OBYC) | GBB-VNG | Scrapping damaged merchandise (mvt 551) | 52400000 |  |
| MM (OBYC) | GBB-VBR | Store supplies consumed to cost center | 63100000 |  |
| MM (OBYC) | GBB-BSA | Initial stock entry at migration (mvt 561) | 13400000 (via BSX) | 39990000 |
| MM (OBYC) | FR1 / FR3 | Freight and duty clearing (planned delivery costs) | 21200100 | 21200100 |
| SD (VKOA) | ERL | POS and online revenue by account assignment group |  | 41000000 / 41000100 |
| SD (VKOA) | ERS | Sales deductions – discounts and coupons | 41200000 |  |
| Tax | MWS | Output sales tax by jurisdiction |  | 22000000 |
| POS inbound | Tender – cash | Store cash takings | 11009400 |  |
| POS inbound | Tender – card | Card takings (acquirer) | 11009500 |  |
| POS inbound | Tender – gift card redemption | Gift card used as tender | 21500000 |  |
| POS inbound | Return (mvt 252) | Customer return – revenue and stock reversed | 41100000 / 13400000 | 11009400 / 50000000 |
| Bank (OT83) | Store deposit | Cash deposited at bank | 11001000 | 11009400 |
| Bank (OT83) | Acquirer settlement | Card settlement net of fees | 11001000 / 63600000 | 11009500 |
| Settlement Mgmt | Condition contract accrual | Vendor rebate accrual per invoice | 12600100 | 52500000 |
| Settlement Mgmt | Condition contract settlement | Rebate settled to vendor (credit memo) | 21100000 | 12600100 |
| Asset Accounting (AO90) | Acquisition / depreciation | Store fit-out and POS hardware | 16300000-16500000 / 64000000-64100000 | 21100000 / 17300000-17500000 |

## 5.13 Financial statement version (FSV US10)

| Node | Line |
| --- | --- |
| 1.1.1 | Cash and cash equivalents |
| 1.1.2 | Trade receivables |
| 1.1.3 | Other current assets |
| 1.1.4 | Vendor receivables and rebates |
| 1.1.5 | Inventories |
| 1.2.1 | Property & equipment |
| 1.2.2 | Right-of-use assets |
| 1.2.3 | Intangible assets |
| 1.2.4 | Deferred tax assets |
| 2.1.1 | Trade payables |
| 2.1.2 | GR/IR clearing |
| 2.1.3 | Accrued and payroll liabilities |
| 2.1.4 | Gift card and customer liabilities |
| 2.1.5 | Refund liabilities |
| 2.1.6 | Lease liabilities – current |
| 2.1.7 | Taxes payable |
| 2.2.1 | Lease liabilities – non-current |
| 2.2.2 | Borrowings |
| 2.2.3 | Deferred tax liabilities |
| 3.1 | Share capital |
| 3.2 | Retained earnings |
| 3.9 | Migration clearing |
| 4.1.1 | Gross sales |
| 4.1.2 | Returns and discounts |
| 4.1.3 | Other revenue |
| 5.1.1 | Cost of goods sold |
| 5.1.2 | Freight and duties |
| 5.1.3 | Price differences |
| 5.1.4 | Shrinkage rebates and markdowns |
| 6.1 | Personnel expenses |
| 6.2 | Occupancy expenses |
| 6.3 | Selling general and administrative |
| 6.4 | Depreciation and amortisation |
| 7.1 | Financial result |
| 8.1 | Income taxes |

Configuration of the chart (OB13, OB62, OBD4, FS00, OB53, OBYC, VKOA, AO90, OB58, document splitting) is in Chapter 6.

# 6. Configuration

Transaction codes and IMG paths are those of SAP S/4HANA Retail; confirm items marked [VERIFY] in your release before build.

## 6.1 Enterprise structure and sites

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Company code, controlling area | OX02 / OKKP | US10 / A000 (shared with finance template) |
| Sales organisation & distribution channels | OVX5 / OVXI | R100; 10 stores, 20 online |
| Purchasing organisation | OX08 | R100 |
| Site categories & profiles | SPRO → Logistics – General → Retailing → Site → Site Profiles [VERIFY] | Z_STORE (category A = store), Z_DC (category B = distribution center), Z_WEB |
| Number ranges for sites | SPRO → Site → Number Ranges [VERIFY] | External: DC01, ST01–ST99 |
| Site master | WB01 / WB02 | Plant data, customer data, supply source, calendar, profit center |
| Plant ↔ company code / sales org | OX18 / OVX6 | All sites → US10; stores → R100/10 |

## 6.2 Merchandise categories and articles

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Merchandise categories | WG21 / WG22 | 11010 Tops & Tees, 11020 Denim, 12010 Shirts, 21010 Cookware |
| Merchandise category hierarchy | SPRO → Merchandise Category → Hierarchy Levels; WMATGRP* [VERIFY] | Levels: division, department, MC |
| Characteristics & class type 026 | CT04 / CL02 | COLOR, SIZE variant-creating; assigned to MC 11010 |
| Article types | OMS2 / MM41 defaults | HAWA, NLAG; field selection per type |
| Article master | MM41 / MM42 / MM43 | Basic, listing, purchasing, sales, logistics DC/store, POS, accounting |
| EAN number ranges & checks | SPRO → Logistics – General → EAN/UPC [VERIFY] | UPC-A / EAN-13 check digit |

## 6.3 Assortment and listing

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Assortment types & listing procedures | SPRO → Assortment → Listing [VERIFY] | Assortment per store cluster (A/B/C) |
| Assortments | WSOA1 / WSOA2 | Z_CLUSTER_A … C; stores assigned |
| Listing | WSP4 (listing conditions) [VERIFY] | Automatic listing by MC and assortment |

## 6.4 Pricing and promotions

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Sales price condition type | V/06 | VKP0 (retail sales price) per distribution chain / site |
| Price calculation schema | SPRO → Pricing → Sales Price Calculation [VERIFY] | Planned markup by MC; price points .99 |
| Price point groups | SPRO → Price Point Groups [VERIFY] | Z_99: 0.99 / 4.99 / 9.99 endings |
| Sales price calculation | VKP5 / VKP2 | Mass calculation and release |
| Promotion types | SPRO → Promotion → Promotion Types [VERIFY] | Z_PROMO with promo price list |
| Promotions | WAK1 / WAK2 | PR-FALL: TS-100 at 15.00, store group A, 2 weeks |

## 6.5 Purchasing, replenishment and allocation

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Vendor BP roles & groupings | BP / BUCF | FLVN00, FLVN01; Y101 |
| Purchasing info records & conditions | ME11 / MEK1 | PB00; vendor discounts |
| Document types | OMEC | NB (standard), UB (stock transport), Z-allocation [VERIFY] |
| Stock transport order setup | SPRO → MM → Purchasing → PO → Set up STO | Shipping data for sites; delivery type NL; mvt 641/101 |
| Replenishment parameters | WR30 / WR60 [VERIFY] | Min/max per store; forecast-based at DC |
| Replenishment run | WRP1R | Daily 22:00 store; weekly DC |
| Allocation tables & rules | WA01 / WA21 [VERIFY] | Store quotas by cluster |
| EDI output | Output Management / NACE | ORDERS05 to vendors |

## 6.6 Store and DC operations

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| EWM warehouse DC01 | /SCWM/LGNUM, /SCWM/MON | Inbound/outbound process types, storage types |
| Store apps | Fiori: receive products, transfer stock, count stock [VERIFY app names] | Roles for store manager/associate |
| Physical inventory | MI01 / MI04 / MI07 or Fiori | Cycle count by MC; tolerance per store |
| Movement types | OMJJ | 251/252 POS sales/returns, 641/101 STO, 701/702 inventory differences |

## 6.7 POS interface

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| POS outbound profile | SPRO → POS Interface → Outbound → Profiles [VERIFY] | Z_STORE: prices, promotions, EAN, merchandise category |
| POS outbound processing | WPMA (manual), WPMI (initialisation) [VERIFY] | Change pointers daily 02:00 |
| POS inbound profile | SPRO → POS Interface → Inbound → Profiles [VERIFY] | WPUUMS (sales aggregated), WPUTAB (tenders), WPUFIB (FI), WPUBON (receipts – optional) |
| POS inbound monitor | WPER | Error handling per store/day |
| CAR / POS DTA | CAR configuration (/POSDW/*) | Inbound TLOG, sales audit tasks, outbound to S/4 |

## 6.8 Vendor rebates

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Condition contract types | SPRO → Settlement Management → Condition Contract [VERIFY] | Z_RBT: purchase rebate, accruals active |
| Condition contracts | WCOCO | CC-0001: vendor 1000700, 3% on purchases |
| Settlement | WB2R_SC | Monthly partial, annual final settlement |

## 6.9 Chart of accounts and finance integration

The account design is in Chapter 5; the settings below create it and connect logistics to the ledger.

| Setting | Transaction / IMG | Value |
| --- | --- | --- |
| Chart of accounts | OB13 | YCOA – operational chart, 8-digit accounts, maintenance language EN |
| Assign chart to company code | OB62 | US10 → YCOA; country chart not used (US) |
| Account groups and number ranges | OBD4 | CASH 11000000–11999999 … SECC 94000000–96999999 (17 groups, see §5.2) |
| Field status variant / groups | OBC4 | Profit center required on P&L and inventory; tax code required on revenue |
| G/L accounts | FS00 / Fiori Manage G/L Account Master Data | 114 accounts from finance/chart_of_accounts.csv (mass load via Migration Cockpit G/L account [VERIFY]) |
| Cost elements | FS00 (type 1 primary / 42 assessment / 43 activity) | P&L accounts as primary cost elements; 94000000–96000000 secondary |
| Retained earnings | OB53 | Key X → 32000000 |
| Financial statement version | OB58 | FSV US10, nodes 1.1.1 … 8.0 as in §5.13 |
| Ledgers and currencies | FINSC_LEDGER | 0L leading (US GAAP); company code currency USD; group currency USD |
| Document splitting | GSP_RD | Splitting characteristics profit center (zero-balance), segment; method 0000000012 |
| Account determination (MM) | OBYC | BSX 13400000; WRX 21200000; PRD 50200000; GBB-VAX 50000000; GBB-INV 52300000; GBB-BSA 39990000 |
| Revenue determination (POS sales) | VKOA | ERL 41000000 (stores), 41000100 (online); ERS 41200000 (POS discounts); MWS 22000000 |
| Tender to G/L mapping | POS inbound FI settings [VERIFY] | Cash → 11009400; card → 11009500; gift card → 21500000 |
| Bank statement rules | OT83 / Manage Bank Statement Reprocessing Rules | Store deposits; acquirer settlement with fee 63600000 |
| Profit center derivation | Site master / document splitting | DC01 → 1100; ST01–ST50 → 2101–2150; WEB1 → 3100 |
| Rebate accounts | Settlement Management account determination [VERIFY] | 12600100 / 52500000 |
| Asset account determination | AO90 | Store fixtures 16400000; accumulated depreciation 17400000; POS & IT 16500000 / 17500000 |
| Migration clearing | FS00 + OBYC GBB-BSA | 39990000 – post-migration balance 0 (blocked for manual posting after go-live) |

Tip: Load the chart of accounts from the same CSV that drives the ETL G/L mapping (etl/config/mapping_rules.yaml) and the worked example – one source of truth for the account design, the migration mapping and the test expectations.

# 7. Integration

| ID | Interface | Direction | Technology | Frequency |
| --- | --- | --- | --- | --- |
| INT-R01 | Prices, promotions, EAN, MC to POS | S/4 → POS | IDoc (WP_PLU, WPDWGR, WP_EAN [VERIFY]) via BTP | Daily 02:00 + ad hoc |
| INT-R02 | TLOG from POS | POS → CAR | File / API | Near real time / end of day |
| INT-R03 | Aggregated sales, tenders, FI | CAR → S/4 | IDoc WPUUMS, WPUTAB, WPUFIB | Daily 01:00–05:00 |
| INT-R04 | Purchase orders | S/4 → vendors | EDI ORDERS via BTP | On PO release |
| INT-R05 | Advance shipping notices | Vendors → S/4/EWM | EDI DESADV | On shipment |
| INT-R06 | Vendor invoices | Vendors → S/4 | EDI INVOIC | On invoice |
| INT-R07 | Bank statements & card settlements | Banks → S/4 | camt.053 / acquirer file | Daily |
| INT-R08 | Online orders & availability | Commerce ↔ S/4 | APIs via BTP | Real time |
| INT-R09 | Analytics | S/4, CAR → SAC/Datasphere | Live / replication | Hourly |

# 8. Finance Integration and Worked Example

This chapter follows one article from purchase to the financial statements. Every amount below is produced and checked by finance/worked_example.py (run in CI): each entry balances, the trial balance balances, the balance sheet balances, all clearing accounts are zero and inventory equals units on hand × moving average cost. All accounts come from the chart of accounts in Chapter 5.

## 8.1 Retail events and their postings

| Event | Movement / document | Debit | Credit |
| --- | --- | --- | --- |
| Vendor goods receipt at DC | 101 / WE | 13400000 Inventory (DC01) | 21200000 GR/IR |
| Vendor invoice | MIRO / RE | 21200000 GR/IR | 21100000 Vendor |
| Rebate accrual | Condition contract | 12600100 Rebate receivable | 52500000 Rebate income |
| Stock transfer DC → store | 641 / 101 | 13400000 (ST01, PC 2101) | 13400000 (DC01, PC 1100) |
| POS sale – stock | 251 | 50000000 COGS | 13400000 Inventory (store) |
| POS sale – revenue & tenders | POS inbound | 11009400 cash, 11009500 card | 41000000 revenue, 22000000 tax |
| POS return | 252 | 41100000 returns, 22000000 tax, 13400000 | 11009400 cash, 50000000 COGS |
| Cash deposit / card settlement | FEBAN | 11001000 bank, 63600000 card fees | 11009400 / 11009500 |
| Inventory difference | 701 / 702 | 52300000 Shrinkage | 13400000 Inventory |
| Initial stock at migration | 561 | 13400000 Inventory | 39990000 Migration clearing |

## 8.2 Scenario

Company code US10 starts with USD 100,000 of capital. It buys 1,000 Basic Tees (generic article TS-100, variants S/M/L) at USD 8 into DC01, moves 600 to store ST01, sells 300 at the regular price of USD 20 and 200 at the promotion price of USD 15 (promotion PR-FALL), accepts 10 returns, counts 5 units of shrinkage, accrues a 3% vendor rebate and pays store payroll and rent. Sales tax is 8%; two thirds of tenders are card (2.5% acquirer fee).

## 8.3 Journal entries

| Step | Transaction | Doc | G/L | Account | Debit | Credit | Assignment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | Migration Cockpit – G/L balances | SA | 11001000 | Bank 1 – Main Account | 100,000.00 |  |  |
|  |  |  | 31000000 | Share Capital |  | 100,000.00 |  |
| R1 | WRP1R / ME21N | — | — | Replenishment proposal and PO: 1000 x TS-100 (variants S/M/L) @ 8 for DC01 – no posting |  |  |  |
| R2 | MIGO 101 / EWM inbound | WE | 13400000 | Inventory – Merchandise (trading goods) | 8,000.00 |  | BSX · site DC01 · PC 1100 |
|  |  |  | 21200000 | GR/IR Clearing – Merchandise |  | 8,000.00 | WRX |
| R3 | MIRO | RE | 21200000 | GR/IR Clearing – Merchandise | 8,000.00 |  | WRX |
|  |  |  | 21100000 | Trade Payables – Domestic |  | 8,000.00 | Vendor 1000700 |
| R4 | Condition contract accrual | SA | 12600100 | Vendor Rebate Receivable (condition contract accruals) | 240.00 |  | Condition contract CC-0001 |
|  |  |  | 52500000 | Vendor Rebate Income (COGS reduction) |  | 240.00 | COGS reduction |
| R5 | F110 | ZP | 21100000 | Trade Payables – Domestic | 8,000.00 |  |  |
|  |  |  | 11001000 | Bank 1 – Main Account |  | 8,000.00 |  |
| D1 | STO · VL10B · VL02N (mvt 641) | WL | 13400000 | Inventory – Merchandise (trading goods) | 4,800.00 |  | Site ST01 · PC 2101 |
|  |  |  | 13400000 | Inventory – Merchandise (trading goods) |  | 4,800.00 | Site DC01 · PC 1100 |
| D2 | Store GR (Fiori, mvt 101) | — | — | Goods receipt in store from stock in transit – value already moved at goods issue |  |  |  |
| S1 | POS inbound WPUUMS (mvt 251) | WA | 50000000 | COGS – Merchandise (stores) | 4,000.00 |  | GBB-VAX · ST01 |
|  |  |  | 13400000 | Inventory – Merchandise (trading goods) |  | 4,000.00 | BSX · ST01 |
| S2 | POS inbound WPUUMS / WPUTAB | RV | 11009400 | Store Cash in Transit | 3,240.00 |  | Tender: cash |
|  |  |  | 11009500 | Payment Card Clearing (acquirer) | 6,480.00 |  | Tender: card |
|  |  |  | 41000000 | Revenue – Merchandise Sales (stores) |  | 9,000.00 | VKOA ERL · ST01 |
|  |  |  | 22000000 | Sales Tax Payable |  | 720.00 | MWS |
| S3 | POS inbound return (mvt 252) | RV | 41100000 | Sales Returns (contra revenue) | 200.00 |  | Sales returns |
|  |  |  | 22000000 | Sales Tax Payable | 16.00 |  |  |
|  |  |  | 11009400 | Store Cash in Transit |  | 216.00 | Cash refund |
|  |  |  | 13400000 | Inventory – Merchandise (trading goods) | 80.00 |  | Mvt 252 · ST01 |
|  |  |  | 50000000 | COGS – Merchandise (stores) |  | 80.00 |  |
| S4 | FEBAN – store deposit | ZB | 11001000 | Bank 1 – Main Account | 3,024.00 |  |  |
|  |  |  | 11009400 | Store Cash in Transit |  | 3,024.00 |  |
| S5 | FEBAN – acquirer settlement | ZB | 11001000 | Bank 1 – Main Account | 6,318.00 |  |  |
|  |  |  | 63600000 | Bank & Payment Card Fees | 162.00 |  | CC store ST01 |
|  |  |  | 11009500 | Payment Card Clearing (acquirer) |  | 6,480.00 |  |
| S6 | Store physical inventory (mvt 702) | WI | 52300000 | Inventory Differences / Shrinkage | 40.00 |  | GBB-INV · ST01 |
|  |  |  | 13400000 | Inventory – Merchandise (trading goods) |  | 40.00 | ST01 |
| O1 | Payroll posting | Y2 | 61000000 | Salaries & Wages – Stores | 1,500.00 |  | CC store ST01 |
|  |  |  | 21400000 | Payroll Clearing |  | 1,500.00 |  |
| O2 | Bank transfer | ZP | 21400000 | Payroll Clearing | 1,500.00 |  |  |
|  |  |  | 11001000 | Bank 1 – Main Account |  | 1,500.00 |  |
| O3 | FB60 | KR | 62000000 | Rent & Occupancy – Stores (variable & short-term) | 1,200.00 |  | CC store ST01 |
|  |  |  | 21150000 | Payables – Landlords |  | 1,200.00 | Landlord 1000800 |
| C1 | FB50 | SA | 79000000 | Income Tax Expense – Current | 554.00 |  | 25% x 2,218 |
|  |  |  | 22200000 | Income Tax Payable |  | 554.00 |  |
|  |  |  |  | Total | 111,698.00 | 111,698.00 |  |

## 8.4 Inventory roll-forward

| Movement | DC01 units | ST01 units | Value (USD) |
| --- | --- | --- | --- |
| Vendor GR | 1000 |  | 8,000.00 |
| STO DC01 → ST01 | −600 | +600 | 0.00 (site transfer) |
| POS sales |  | −500 | (4,000.00) |
| POS returns |  | +10 | 80.00 |
| Shrinkage |  | −5 | (40.00) |
| Closing | 400 | 105 | 4,040.00 |

## 8.5 Trial balance

| G/L account | Description | FSV | Debit | Credit |
| --- | --- | --- | --- | --- |
| 11001000 | Bank 1 – Main Account | 1.1.1 | 99,842.00 |  |
| 12600100 | Vendor Rebate Receivable (condition contract accruals) | 1.1.4 | 240.00 |  |
| 13400000 | Inventory – Merchandise (trading goods) | 1.1.5 | 4,040.00 |  |
| 21150000 | Payables – Landlords | 2.1.1 |  | 1,200.00 |
| 22000000 | Sales Tax Payable | 2.1.7 |  | 704.00 |
| 22200000 | Income Tax Payable | 2.1.7 |  | 554.00 |
| 31000000 | Share Capital | 3.1 |  | 100,000.00 |
| 41000000 | Revenue – Merchandise Sales (stores) | 4.1.1 |  | 9,000.00 |
| 41100000 | Sales Returns (contra revenue) | 4.1.2 | 200.00 |  |
| 50000000 | COGS – Merchandise (stores) | 5.1.1 | 3,920.00 |  |
| 52300000 | Inventory Differences / Shrinkage | 5.1.4 | 40.00 |  |
| 52500000 | Vendor Rebate Income (COGS reduction) | 5.1.4 |  | 240.00 |
| 61000000 | Salaries & Wages – Stores | 6.1 | 1,500.00 |  |
| 62000000 | Rent & Occupancy – Stores (variable & short-term) | 6.2 | 1,200.00 |  |
| 63600000 | Bank & Payment Card Fees | 6.3 | 162.00 |  |
| 79000000 | Income Tax Expense – Current | 8.1 | 554.00 |  |
|  | Total |  | 111,698.00 | 111,698.00 |

## 8.6 Income statement (store ST01 = company in this example)

| Line | USD |
| --- | --- |
| Gross sales (41000000) | 9,000.00 |
| Returns (41100000) | (200.00) |
| Net sales | 8,800.00 |
| Cost of goods sold at moving average cost (50000000) | (3,920.00) |
| Vendor rebate income (52500000) | 240.00 |
| Shrinkage (52300000) | (40.00) |
| Gross margin | 5,080.00 |
| Store payroll (61000000) | (1,500.00) |
| Store rent (62000000) | (1,200.00) |
| Card fees (63600000) | (162.00) |
| Profit before tax | 2,218.00 |
| Income tax 25% (79000000) | (554.00) |
| Net income | 1,664.00 |

## 8.7 Balance sheet

| Line | USD |
| --- | --- |
| Cash and bank (11001000) | 99,842.00 |
| Vendor rebate receivable (12600100) | 240.00 |
| Inventory – DC01 400 + ST01 105 units × 8 (13400000) | 4,040.00 |
| Total assets | 104,122.00 |
| Payables – landlord (21150000) | 1,200.00 |
| Sales tax payable (22000000) | 704.00 |
| Income tax payable (22200000) | 554.00 |
| Total liabilities | 2,458.00 |
| Share capital (31000000) | 100,000.00 |
| Net income for the period | 1,664.00 |
| Total equity | 101,664.00 |
| Total liabilities and equity | 104,122.00 |

Checks (automated): assets 104,122.00 = liabilities 2,458.00 + equity 101,664.00. GR/IR (21200000), store cash in transit (11009400) and card clearing (11009500) are zero because every receipt, deposit and settlement has been matched – the target daily state for every store.

## 8.8 Store KPIs from the example

| KPI | Value |
| --- | --- |
| Net sales ST01 | 8,800.00 |
| Gross margin % | 57.7% |
| Promotion share of units | 40% |
| Shrinkage % of net sales | 0.45% |
| Return rate (units) | 2.0% |
| Sell-through ST01 | 82% |

## 8.9 Daily finance controls in production

| Control | Account / report | Target |
| --- | --- | --- |
| POS cash takings deposited | 11009400 Store cash in transit by store | 0 after bank statement |
| Card settlements received | 11009500 Payment card clearing | 0 after acquirer file |
| Goods received = invoiced | 21200000 GR/IR | Ageing < 30 days |
| Rebates accrued | 12600100 vs condition contract | Accrual = contract rate × invoiced value |
| Store stock accuracy | 52300000 Shrinkage by store and MC | < 1.5% of sales |
| Migration clearing | 39990000 | 0 from go-live onwards |

# 9. Testing

## 9.1 Test strategy

| Test phase | Scope | Environment | Entry / exit criteria | Owner |
| --- | --- | --- | --- | --- |
| Unit test | Each configuration item & development object | DEV | Config complete / test evidence in ALM | Functional consultant |
| String test | Process segments (e.g. PO → GR → invoice) | DEV/QA | Unit tests passed / no sev-1 | Workstream lead |
| SIT 1 | End-to-end processes incl. interfaces with test POS and EDI | QA | Mock load 1 data / ≥ 95% pass, no sev-1 | Test lead |
| SIT 2 | Full scope incl. CAR, EWM, banks, month-end close | QA | Mock load 2 / 100% executed, no sev-1/2 | Test lead |
| Performance | POS inbound volume, replenishment run, POS outbound, EWM waves | PRE-PROD | Production-size data / NFR-01–03 met | Basis / test lead |
| UAT | Business acceptance per role, day-in-the-life of store & DC | QA | SIT exit / business sign-off | Business process owners |
| Store pilot rehearsal | Model store with real POS terminals, scanners, printers | QA + lab store | Devices certified / 3 trading days simulated | Store operations |
| Regression | Automated core scenarios after each transport wave | QA | Before each release | Test automation |
| Cutover rehearsal | Full cutover runbook incl. timings | PRE-PROD | Mock 3 / within cutover window | Cutover manager |

## 9.2 Integration test scenarios

| ID | Scenario | Expected result |
| --- | --- | --- |
| SIT-R01 | Create generic article with variants, list to cluster A, calculate price, download to POS | Variants & EANs created; listed in 20 stores; price 19.99 rounded; POS file contains article |
| SIT-R02 | DC replenishment → PO → EDI ORDERS → DESADV → EWM GR → EDI INVOIC → MIRO | GR value 8,000.00; invoice matched; rebate accrual 240.00 |
| SIT-R03 | Store replenishment → STO → EWM pick → GI 641 → store GR (Fiori) | Inventory value 4,800.00 moves to ST01 / PC 2101 |
| SIT-R04 | Promotion PR-FALL created and active at POS on start date | POS sells at 15.00 in cluster A only |
| SIT-R05 | POS day with sales, return, cash and card tenders → CAR audit → S/4 | Revenue 8,800.00; COGS 3,920.00; tenders cleared |
| SIT-R06 | POS IDoc error (unknown EAN) → correction in CAR → reprocess | Error visible in WPER/CAR; reprocessed successfully |
| SIT-R07 | Store cycle count with difference | Shrinkage 40.00 posted to 52300000 / store |
| SIT-R08 | Card acquirer settlement & cash deposit bank statement | Auto-matched; fee to 63600000 |
| SIT-R09 | Allocation of new season article to stores by cluster quota | STOs per store as per allocation table |
| SIT-R10 | Online order fulfilled from DC; customer return to store | Stock & revenue posted in correct sites |
| SIT-R11 | Condition contract settlement | Settlement document credits vendor; receivable cleared |
| SIT-FIN-01 | Month-end close and store P&L | Net income 1,664.00; balance sheet balances (§8.7) |

## 9.3 Defect management

| Severity | Definition | Resolution target |
| --- | --- | --- |
| 1 – Critical | Blocks trading, POS posting or payments; no workaround | 4 hours, fix before next test day |
| 2 – High | Major function impaired; workaround hard | 2 days |
| 3 – Medium | Function impaired; workaround exists | Before UAT exit |
| 4 – Low | Cosmetic | Backlog |

# 10. Data Migration – Azure ETL to the SAP Migration Cockpit

Legacy merchandising, POS back-office and finance data is extracted, cleansed and transformed in Microsoft Azure and loaded into the staging tables of the SAP S/4HANA Migration Cockpit in the SAP HANA database. The Migration Cockpit then performs the final, validated transfer into S/4HANA through its standard migration objects and APIs. Azure does the heavy lifting (profiling, mapping, de-duplication, GS1 checks, reconciliation and repeatable mock runs); SAP keeps control of the business-logic checks and the posting into the application.

A working reference implementation is in etl/: Bicep infrastructure, Data Factory pipelines, Databricks notebooks, a tested Python transformation library, control-database SQL and a sample run with deliberate data defects.

Figure 10-1. Azure ETL architecture – legacy → ADF → ADLS bronze/silver/gold (Databricks) → HANA staging → Migration Cockpit → S/4HANA

## 10.1 Migration approach

| Decision | Choice | Rationale |
| --- | --- | --- |
| Migration approach | New implementation (greenfield) of S/4HANA Retail; legacy is non-SAP | Clean master data and new merchandise category design |
| Transfer method | Migration Cockpit – Migrate Data Using Staging Tables | Volume (articles × variants × sites), repeatable loads, DB-level population from an external ETL |
| ETL platform | Azure Data Factory + Azure Databricks + ADLS Gen2 | Client standard cloud; scales for POS history; Git-versioned, testable code |
| Staging connection | Databricks → SAP HANA JDBC (ngdbc) into the staging schema; alternative: ADF copy via ODBC on the self-hosted IR | Staging tables are plain HANA tables; truncate + insert per object per run |
| Data quality | Rules in code (retail_etl) with results in Azure SQL and Power BI | DQ worklist for data owners; objective load gate |
| Reconciliation | Source → gold (Azure) and gold → S/4HANA (OData / CDS) | Two-stage proof: nothing lost in transformation, nothing lost in the load |
| What is not migrated | Closed POs, POS transactions (24 months of sales history loaded to CAR/forecasting separately), history of prices | Keeps cutover window to one night |

## 10.2 End-to-end flow

Figure 10-2. Pipeline sequence with the data-quality gate

## 10.3 Azure components

| Component | Purpose | Implementation |
| --- | --- | --- |
| Self-hosted integration runtime | Secure access from Azure to on-premises legacy SQL Server and file shares | shir-onprem, registered in ADF |
| Azure Data Factory | Orchestration, extract copy, DQ gate, logging, retries | etl/adf/pipeline – pl_00_master_migration runs pl_10 → pl_20 → pl_30 → pl_40 |
| ADLS Gen2 | Medallion lake: bronze raw Parquet per run_id, silver cleansed Delta, gold SAP staging layout, archive | HNS enabled, ZRS, public access disabled, private endpoints |
| Azure Databricks | PySpark transformations calling the shared retail_etl library; HANA JDBC load | etl/databricks notebooks 01–04 |
| Azure SQL (control DB) | Object catalogue and load order, value mappings, run log, DQ results, reconciliation, readiness view | etl/sql/azure_sql |
| Key Vault | Legacy, HANA and S/4 credentials; accessed by managed identity | Secret scope kv-migration |
| Log Analytics | ADF / Databricks diagnostics and alerts | Diagnostic settings in Bicep |
| Power BI | Migration dashboard: DQ worklist per data owner, load readiness, reconciliation | Reads etl.v_load_readiness, etl.dq_result, etl.recon_result |
| Infrastructure as code | Repeatable environments (dev / test / prod migration) | etl/infra/main.bicep |

## 10.4 Medallion layers

| Layer | Content | Rules |
| --- | --- | --- |
| Bronze | Exact copy of the legacy extract, partitioned by run_id (MOCK1, MOCK2, MOCK3, CUTOVER) | Immutable; kept for audit |
| Silver | Typed, trimmed, de-duplicated legacy data in legacy structure | Technical cleansing only – no business mapping |
| Gold | One table per migration object, SAP technical field names, values mapped to S/4HANA | Business mapping, GS1 checks, generic/variant build, 561 stock, G/L mapping; rejected rows go to DQ, never silently dropped |

## 10.5 Transformation rules (silver → gold)

| Object | Key transformation | Code |
| --- | --- | --- |
| Site | Store / DC / web → site category VLFKZ A (store) / B (DC), site profile Z_STORE / Z_DC / Z_WEB; profit center DC01 → 1100, STnn → 21nn, WEB1 → 3100; ZIP zero-padded | transform.sites |
| Supplier | Vendor → Business Partner (grouping Y101), reconciliation account 21100000, purchasing org R100; duplicate tax ID = ERROR, missing bank = WARNING + payment block | transform.suppliers |
| Article | Legacy style → generic article (ATTYP 01), each colour/size SKU → variant (ATTYP 02); department/class → merchandise category (e.g. 10-100 → 11010); UPC checked with the GS1 check digit; EAN category UC (12-digit) / HE | transform.articles, quality.gtin_check_digit |
| Sales price | Retail price → VKP0 condition per sales org R100 / channel 10, valid from go-live; WARNING for price points not ending .99/.00 and price below cost | transform.sales_prices |
| Inventory balance | Post-count on-hand → movement type 561 per site / storage location 0001, value = quantity × moving average cost; ERROR for unknown site/article and negative stock | transform.inventory_balances |
| G/L balance | Legacy account → YCOA account via mapping_rules.yaml; legacy inventory account re-pointed to 39990000 because the 561 stock load already posts inventory; trial balance must balance | transform.gl_balances |

All mappings are configuration, not code: etl/config/mapping_rules.yaml and the map.value_mapping table in the control database (approved by the data owner for each object).

## 10.6 Data quality gate

| Severity | Meaning | Effect |
| --- | --- | --- |
| ERROR | The record would fail or corrupt S/4HANA (invalid / duplicate GTIN, unmapped merchandise category, unknown site, negative stock, duplicate supplier) | Excluded from gold, reported to the data owner. Cutover run requires zero open ERRORs |
| WARNING | Loadable but needs business attention (price point, missing bank details) | Loaded; on the worklist |
| Reconciliation FAIL | Totals do not agree (rows, stock value, migration clearing) | ADF Fail activity – nothing is loaded to HANA |

pl_20_transform evaluates the gate. In mock runs the parameter allow_dq_errors = true lets valid records through so the Migration Cockpit can be tested while defects are fixed; for the cutover run it is false.

Sample run (fictitious legacy extract with deliberate defects – etl/sample_output):

| Object | Severity | Findings | Examples |
| --- | --- | --- | --- |
| article | ERROR | 4 | UPC fails GS1 check digit; duplicate UPC; department 90-900 not mapped |
| inventory_balance | ERROR | 25 | Stock for rejected articles; negative on-hand |
| sales_price | WARNING | 2 | Price point not ending .99 / .00 |
| supplier | ERROR | 2 | Two vendors share one tax ID – merge before load |
| supplier | WARNING | 1 | No bank details – payment block until four-eyes verification |

| Reconciliation check | Expected | Actual | Status |
| --- | --- | --- | --- |
| Site: source rows = gold + rejected | 7 | 7 | PASS |
| Supplier: source rows = gold + rejected | 5 | 5 | PASS |
| Article: source variants = gold variants + rejected | 13 | 13 | PASS |
| Stock value (561) = legacy G/L inventory | 15,520.00 | 15,520.00 | PASS |
| Migration clearing 39990000 nets to zero | 0.00 | 0.00 | PASS |

## 10.7 Loading the Migration Cockpit staging tables

- Create the migration project in the Fiori app Migrate Your Data – Migration Cockpit, method Migrate Data Using Staging Tables, with a database connection to the staging schema (same HANA database or a remote one) [VERIFY] for your release.

- Select migration objects (Site, Supplier, Article, Condition record for pricing in sales, Material inventory balance, G/L account balance …). The cockpit generates one staging table per structure (names such as /1LT/DS_MGRxxx…).

- Record the generated table names in etl/config/staging_tables.yaml and compare each staging structure with the gold layout (download the staging template).

- Load staging: pl_30_load_hana_staging reads the object catalogue in load order and runs notebook 03_load_hana_staging per object – truncate, then batched insert over JDBC with the technical user MIG_LOADER (password from Key Vault).

- Prepare and map values in the cockpit (e.g. legacy UoM, country, merchandise category if not mapped in Azure) – most mapping is already done in gold, so the cockpit mapping tasks are confirmations.

- Simulate each object (no posting; full application checks) and fix errors at source → re-run the pipeline.

- Migrate in load order; the cockpit records status per staging record (processed, error).

- Reconcile: pl_40_reconcile runs notebook 04_reconcile_target, reading S/4HANA OData / CDS views (articles, sites, stock by site, G/L balances) and comparing them with the gold control totals.

Important: Staging table names, structures and the available migration objects differ by S/4HANA release and are generated per project. Never hard-code them – keep them in configuration and re-check after each upgrade or project copy.

## 10.8 Migration object sequence

| Load | Object | Migration Cockpit object | Azure gold | Dependency | Validation |
| --- | --- | --- | --- | --- | --- |
| 1 | Sites (DC, stores, web) | Site [VERIFY] | site | Org structure configured | Site count; profit center |
| 2 | Merchandise categories & hierarchy | Configuration / upload [VERIFY] | (config) | — | Hierarchy compare |
| 3 | Suppliers (BP, bank) | Supplier | supplier | — | Count; bank four-eyes check |
| 4 | Articles (generic, variants, EANs) | Article [VERIFY] | article | 2, 3 | Count by MC; EAN uniqueness |
| 5 | Purchasing info records | Purchasing info record | (phase 2 of ETL) | 3, 4 | Cost sample |
| 6 | Listings / assortments | Upload [VERIFY] | (phase 2 of ETL) | 1, 4 | Article–site count |
| 7 | Sales prices (VKP0) | Condition record for pricing in sales | sales_price | 4, 6 | Price compare vs legacy POS |
| 8–11 | Promotions, replenishment parameters, condition contracts, POS initialisation | Manual / upload / WPMI | — | 7 | Business sign-off |
| 12 | Stock balances DC & stores (from count) | Material inventory balance (561) | inventory_balance | 1, 4 | Qty & value = count × cost |
| 13 | Open POs and STOs | Purchase order (only open) | (phase 2 of ETL) | 3, 4 | Open qty / value |
| 14 | G/L balances, open AP/AR | G/L account balance; open items | gl_balance | 12 | TB = legacy; 39990000 = 0 |

## 10.9 Financial reconciliation of the migration

The initial stock load (561) posts Dr 13400000 Inventory / Cr 39990000 Migration clearing (OBYC GBB-BSA). The G/L balance load posts all other legacy balances and Dr 39990000 for the legacy inventory balance (the ETL re-points the legacy inventory account to 39990000). After both loads, 39990000 must be zero; any difference is a stock-vs-ledger difference that finance must explain before go/no-go.

| Step | Dr | Cr | Amount (sample) |
| --- | --- | --- | --- |
| Stock load 561 | 13400000 Inventory | 39990000 Migration clearing | 15,520.00 |
| G/L balance – inventory line | 39990000 Migration clearing | (offset in balance load) | 15,520.00 |
| 39990000 balance |  |  | 0.00 |

## 10.10 Mock loads

| Mock | Environment | Data | Run parameters | Exit criteria |
| --- | --- | --- | --- | --- |
| Mock 1 | QA | Pilot stores + DC, 20% of articles | run_id=MOCK1, allow_dq_errors=true | ≥ 90% load success; DQ worklist issued |
| Mock 2 | QA | All stores, all articles | MOCK2, allow_dq_errors=true | ≥ 98%; price and stock reconcile |
| Mock 3 / dress rehearsal | PRE-PROD | Full volume, cutover timings | MOCK3, allow_dq_errors=false | ≥ 99.5%; zero ERRORs; within cutover window |
| Cutover | PROD | Full volume after physical count | CUTOVER, allow_dq_errors=false | Reconciliation PASS; sign-off by data owners and finance |

Important: Article and EAN quality is the biggest migration risk in retail. The GS1, duplicate-EAN and unmapped-MC checks run in every mock; no article may go live without an EAN, merchandise category, listing and price.

## 10.11 Roles and security

| Topic | Design |
| --- | --- |
| Data ownership | Each object has a business data owner in etl.migration_object who signs off the DQ worklist and reconciliation |
| Credentials | Only in Key Vault; ADF and Databricks use managed identities |
| Network | Private endpoints for ADLS, SQL, Key Vault, Databricks; SHIR outbound only |
| Personal data | Supplier bank details encrypted at rest; lake access by Entra ID groups; bronze retention ends 90 days after go-live |
| HANA user | MIG_LOADER with write access only to the staging schema |
| Audit | Every run logged in etl.run_log with run_id, row counts and user |

# 11. Cutover

Figure 11-1. Cutover timeline

## 11.1 Cutover strategy

- Pilot then waves: DC01 and 5 pilot stores go live first; remaining 45 stores in waves of 10–15 stores per week. Until a store migrates, its POS continues on legacy; DC01 supplies both.

- Go-live on a Sunday night after store close, before the lowest-volume trading day.

- Stock baseline by physical count in DC and stores, loaded at count cost.

- Freeze periods: master data freeze T-14; price and promotion freeze T-7 (only emergency changes); no new POs in legacy from T-3.

## 11.2 Cutover runbook (excerpt)

| # | Time | Task | Owner | Dependency |
| --- | --- | --- | --- | --- |
| 1 | T-14 | Freeze article, vendor and site changes in legacy | Master data lead | — |
| 2 | T-13 … T-8 | Load sites, MCs, vendors, articles, info records, listings (objects 1–6) | Data migration lead | 1 |
| 3 | T-7 | Load prices, promotions, replenishment parameters, rebates (7–10) | Pricing / buying | 2 |
| 4 | T-4 | POS outbound initialisation; verify price files on pilot terminals | POS lead | 3 |
| 5 | T-3 | Last legacy POs; legacy invoice cut-off | Buying / AP | — |
| 6 | T-2 (after close) | Physical count DC01 and pilot stores | Store & DC managers | 5 |
| 7 | T-1 | Load stock, open POs/STOs, AP/AR, G/L balances; reconcile | Data migration / finance | 6 |
| 8 | T-1 20:00 | Go / no-go meeting | Steering committee | 7 |
| 9 | T-0 06:00 | Open stores on S/4 prices; POS sends TLOG to CAR | Store operations | 8 |
| 10 | T+1 01:00 | First POS inbound run; first replenishment run | Hypercare team | 9 |

## 11.3 Go / no-go criteria

| Criterion | Threshold |
| --- | --- |
| Stock load reconciled to count | 100% of sites; value difference < 0.1% |
| Article, EAN, price completeness | 100% of listed articles have EAN, price and listing |
| POS outbound verified on pilot terminals | Sample of 200 articles per store scanned correctly |
| Open sev-1 / sev-2 defects | 0 / ≤ 3 with workaround |
| Users trained & authorised | ≥ 95% of store and DC users |
| Hypercare staffed | War room, service desk and store champions confirmed |
| Rollback plan | Legacy POS and merchandising available for 2 weeks |

# 12. Go-Live, Hypercare and Production

## 12.1 First-week checklist

| Day | Checkpoint | Owner |
| --- | --- | --- |
| Day 1 morning | All pilot stores open; POS prices correct; first sales scanned | Store ops / POS lead |
| Day 1 evening | End-of-day TLOG received in CAR for every store | CAR lead |
| Day 2 06:00 | POS inbound processed; store sales posted; no WPER errors outstanding | Hypercare |
| Day 2 | Replenishment run created STOs; DC wave picked and shipped | Supply chain |
| Day 3 | Store GR of first DC deliveries; in-transit stock clears | Stores |
| Day 3–5 | Bank statements matched for cash & card | Finance |
| Day 5 | First weekly store P&L reviewed | Finance / merchandising |
| Day 7 | Wave 2 readiness review | PMO |

## 12.2 Rollout waves

| Wave | Sites | Timing | Entry criteria |
| --- | --- | --- | --- |
| Pilot | DC01 + ST01–ST05 | Week 52 | Go/no-go passed |
| Wave 1 | ST06–ST20 | Week 55 | Pilot stable 2 weeks; KPIs green |
| Wave 2 | ST21–ST35 | Week 58 | Wave 1 stable |
| Wave 3 | ST36–ST50 + WEB1 | Week 61 | Wave 2 stable |

## 12.3 Hypercare organisation

Figure 12-2. Hypercare organisation

## 12.4 Hypercare model

| Element | Design |
| --- | --- |
| Duration | 4 weeks after pilot; 2 weeks after each wave (overlapping) |
| War room | Daily 08:00 stand-up; functional, integration, Basis, CAR, EWM and business leads |
| Store support | Store champions in every store; floor-walkers in pilot stores for first 3 days |
| Service desk | Extended hours 06:00–23:00 incl. weekends; retail ticket categories |
| Escalation | Sev-1 to hypercare lead within 15 minutes; SAP incident for product defects |

## 12.5 Hypercare KPIs

| KPI | Target | Source |
| --- | --- | --- |
| POS inbound IDocs in error at 06:00 | 0 | WPER / CAR |
| Stores with missing TLOG | 0 | CAR monitor |
| Price discrepancies reported by stores | < 5 per day (pilot) | Service desk |
| Replenishment run completed by 23:30 | 100% | Job monitor |
| Store GR within 24 h of DC GI | ≥ 95% | In-transit stock report |
| Bank statement auto-match | ≥ 95% | FEBAN |
| Open sev-1 / sev-2 tickets | 0 / < 5 | ITSM |

## 12.6 Exit criteria

- Two consecutive weeks with all hypercare KPIs green.

- No open sev-1 tickets; sev-2 tickets have agreed fix dates.

- First month-end close completed by WD+4 with store P&Ls.

- Knowledge transfer to the support organisation signed off; runbooks and job schedule handed over.

## 12.7 Daily batch schedule

| Time | Job | Purpose | Owner |
| --- | --- | --- | --- |
| 01:00 | CAR outbound to S/4 (aggregated sales) | Post store sales | CAR / Basis |
| 01:30–05:00 | POS inbound processing (WPUUMS, WPUTAB, WPUFIB) | Stock, revenue, tenders | Basis |
| 02:00 | POS outbound change pointers (WPMA job) | Prices & promotions to POS | Basis |
| 05:00 | POS error check (WPER) & alert | Ensure completeness | Hypercare / AMS |
| 06:00 | Bank statement import | Cash & card reconciliation | Finance |
| 22:00 | Store replenishment run (WRP1R) | Create STOs | Supply chain |
| 22:30 | STO → delivery creation (VL10B job) | DC waves | Supply chain |
| Weekly | DC replenishment / forecast | Vendor POs | Buying |
| Monthly | Rebate partial settlement (WB2R_SC); close tasks | Rebates & close | Finance |

## 12.8 Support model

| Tier | Scope | Provider |
| --- | --- | --- |
| L0 | Store champions, knowledge base | Business |
| L1 | Service desk, password/role, triage | [SERVICE_DESK] |
| L2 | Retail functional (merchandising, POS, replenishment, finance) | Retail CoE / [AMS_PROVIDER] |
| L3 | Development, integration, Basis | [AMS_PROVIDER] |
| L4 | SAP product support | SAP |

## 12.9 Continuous improvement

- Monthly review of POS errors, price discrepancies and replenishment accuracy by store.

- Quarterly release for enhancements and SAP Feature Pack adoption.

- Phase 2 backlog: fashion seasons, unified demand forecast, markdown optimisation, loyalty.

# 13. Project Plan, Governance and Risks

Figure 13-1. Implementation roadmap

## 13.0 Timeline (SAP Activate)

Illustrative start date 4 January 2027 – shift to the actual project start.

## 13.1 Workstreams

| Workstream | Scope | Lead |
| --- | --- | --- |
| Merchandise master data | MC, articles, sites, vendors, listing | [MD_LEAD] |
| Pricing & promotions | Price calculation, promotions, POS outbound | [PRICING_LEAD] |
| Buying & replenishment | Purchasing, replenishment, allocation, rebates | [BUY_LEAD] |
| DC & store operations | EWM, store apps, inventory | [OPS_LEAD] |
| POS & CAR | POS interface, sales audit, devices | [POS_LEAD] |
| Finance | FI/CO, valuation, cash & card, close | [FIN_LEAD] |
| Data migration | Objects, mocks, reconciliation | [DM_LEAD] |
| Integration & technology | BTP, EDI, Basis, security | [TECH_LEAD] |
| Change & training | Store training, communications, store champions | [OCM_LEAD] |
| Test & cutover | Test management, cutover runbook | [TEST_LEAD] |

## 13.2 RACI

| Activity | Sponsor | Merch. GPO | Ops GPO | Finance GPO | Workstream lead | SI partner | IT | Store ops |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements sign-off | A | R | R | R | C | C | I | C |
| Solution design | I | A | C | C | R | R | C | C |
| Configuration build | I | C | C | C | A | R | C | I |
| Data cleansing | I | A | R | R | C | C | I | R |
| Mock loads & reconciliation | I | C | C | A | R | R | R | I |
| UAT sign-off | I | A | A | A | R | C | I | R |
| Cutover execution | I | C | C | C | R | R | A | R |
| Go / no-go | A | R | R | R | C | C | C | C |
| Hypercare | I | C | C | C | R | R | A | R |

## 13.3 Key risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Poor article/EAN data quality | Wrong prices, unsellable items | Early cleansing, EAN checks in every mock, data owners per MC |
| POS integration volume / timing | Late store P&L, stock errors | Performance test at full volume; aggregation in CAR |
| Store adoption | Manual workarounds | Store champions, floor-walkers, simple Fiori apps |
| Promotion complexity | Price errors at POS | Limit promotion types in phase 1; regression tests |
| Peak season timing | Business disruption | No go-live in Nov–Dec; freeze periods |
| Legacy coexistence during waves | Supply and reporting gaps | DC supplies both; interim reporting bridge |
| Legacy data quality blocks the Azure ETL load gate at cutover | Go-live delay | DQ worklists from Mock 1 onward; data owners sign off per object; zero-ERROR target by Mock 3 |
| Migration Cockpit staging structures change after an upgrade or project copy | Failed staging load | Staging table names in configuration; template comparison step in every mock |

# 14. Glossary of Abbreviations and Terms

## 14.1 Abbreviations

| Abbreviation | Meaning |
| --- | --- |
| AA | Asset Accounting (SAP FI-AA) |
| ADF | Azure Data Factory – cloud orchestration and data movement service |
| ADLS Gen2 | Azure Data Lake Storage Gen2 – hierarchical-namespace storage for the data lake |
| AMS | Application Management Services – post-go-live support provider |
| AP / AR | Accounts Payable / Accounts Receivable |
| ATTYP | Article category field (00 single, 01 generic, 02 variant, 10 sales set, 11 prepack) |
| BP | Business Partner – S/4HANA master record for suppliers and customers |
| BR | Business requirement (IDs BR-xx-nn in Chapter 2) |
| BSX / WRX / PRD / GBB | OBYC transaction keys: inventory posting / GR/IR clearing / price differences / offsetting entry for inventory posting |
| BTP | SAP Business Technology Platform (Integration Suite for interfaces) |
| CAR | SAP Customer Activity Repository – POS data hub with sales audit (POS DTA) |
| CDS | Core Data Services – S/4HANA virtual data model views used for reporting and reconciliation |
| CO | Controlling (cost centers, profit centers, internal orders) |
| COGS | Cost of goods sold |
| CoA | Chart of accounts |
| DC | Distribution center (site category B) |
| DESADV / ORDERS / INVOIC | EDI messages: despatch advice / purchase order / invoice |
| DQ | Data quality |
| DTA | Data Transfer and Audit (POS DTA in CAR) |
| EAN / GTIN / UPC | European Article Number / Global Trade Item Number / Universal Product Code – barcode identifiers (GS1) |
| EDI | Electronic Data Interchange |
| ERL / ERS / MWS | VKOA account keys: revenue / sales deductions / output tax |
| ETL | Extract, transform, load |
| EWM | SAP Extended Warehouse Management |
| FI | Financial Accounting |
| FSV | Financial statement version |
| GI / GR | Goods issue / goods receipt |
| GR/IR | Goods receipt / invoice receipt clearing account |
| GS1 | Global standards body for barcodes; defines the GTIN check digit |
| HANA | SAP in-memory database underlying S/4HANA |
| IDoc | Intermediate Document – SAP message format (e.g. WPUUMS, WPUTAB, WPUFIB for POS inbound) |
| IMG / SPRO | Implementation Guide – SAP configuration menu |
| IR / SHIR | (Self-hosted) integration runtime in Azure Data Factory |
| IS-Retail | SAP Industry Solution Retail – in S/4HANA: SAP S/4HANA Retail for merchandise management |
| JDBC / ODBC | Database connectivity standards used to write to HANA staging tables |
| KPI | Key performance indicator |
| MC | Merchandise category |
| MIGO / MIRO | Goods movement / supplier invoice transactions |
| NRV | Net realisable value |
| OBYC / VKOA | Account determination for inventory postings / for revenue (SD and POS) |
| OData | Open Data Protocol – REST API used to read S/4HANA for reconciliation |
| P&L | Profit and loss statement |
| PO / STO | Purchase order / stock transport order |
| POS | Point of sale |
| RACI | Responsible, Accountable, Consulted, Informed |
| RF | Radio frequency (handheld scanner in DC) |
| ROU | Right-of-use asset (leases) |
| SIT / UAT | System integration test / user acceptance test |
| SKU | Stock keeping unit – a variant article |
| TLOG | Transaction log – POS sales file from the till |
| VKP0 | Standard sales price condition type in retail |
| VLFKZ | Site category field (A = store, B = distribution center) |
| WD+n | Working day n of the next month (close calendar) |
| YCOA | SAP Best Practices operational chart of accounts |

## 14.2 Terms

| Term | Meaning |
| --- | --- |
| Allocation | Distribution of a quantity of merchandise (e.g. new season, promotion) to stores by rules |
| Assortment / listing | The set of articles a site may sell; listing creates the article–site link required for POS and replenishment |
| Bronze / silver / gold | Medallion lake layers: raw copy / cleansed legacy structure / SAP-ready migration layout |
| Condition contract | Settlement Management agreement with a vendor for rebates and funding; accrues on invoices and settles periodically |
| Cutover | The controlled sequence of freeze, final loads, count and switch from legacy to S/4HANA |
| Document splitting | Real-time splitting of G/L lines by profit center/segment so each store has a balanced balance sheet |
| Generic article | Parent article (e.g. TS-100 Basic Tee) carrying common data; its variants are colour/size combinations |
| Go / no-go | Formal decision meeting before go-live against agreed criteria |
| Hypercare | Intensive support period after go-live with war room and KPIs |
| Load gate | Automated decision in ADF that allows the HANA staging load only if DQ and reconciliation pass |
| Medallion architecture | Layered lakehouse design (bronze → silver → gold) |
| Migration Cockpit | S/4HANA tool for data migration (Fiori app Migrate Your Data), using files or staging tables |
| Migration clearing account | 39990000 – technical account that balances the stock and G/L loads; must be zero after migration |
| Mock load | Full rehearsal of the migration in a test system |
| Moving average cost | Inventory valuation where the unit cost is recalculated on each receipt (price control V) |
| Price point | Customer-facing price ending (.99, .00) applied by price calculation |
| Profit center | CO object per store/DC used for store P&L and balance sheet |
| Replenishment | Automatic calculation of order quantities for DC (from vendors) and stores (from DC) |
| Sales audit | Validation and correction of POS data in CAR before posting to S/4HANA |
| Shrinkage | Unexplained inventory loss found by counts (theft, damage, errors) |
| Site | Retail plant: store, DC or online channel, created from a site profile |
| Staging table | HANA table generated by the Migration Cockpit and filled by the ETL before the migration run |
| Tender | Means of payment at POS (cash, card, gift card) |
| Variant | Saleable colour/size version of a generic article with its own EAN |
| Wave | Group of stores going live together after the pilot |

# Appendix A. Transaction Code Index

| Area | Transactions / apps |
| --- | --- |
| Sites | WB01, WB02, WB03 |
| Merchandise categories & articles | WG21, WG22, CT04, CL02, MM41, MM42, MM43 |
| Assortment & listing | WSOA1, WSOA2, WSP4 [VERIFY] |
| Pricing & promotions | VKP5, VKP2, V/06, WAK1, WAK2 |
| Purchasing & replenishment | ME21N, ME11, WRP1R, WA01, VL10B |
| Inventory & stores | MIGO, MI01, MI04, MI07, Fiori store apps |
| POS | WPMA, WPMI, WPER, CAR /POSDW/* |
| Rebates | WCOCO, WB2R_SC |
| Finance | MIRO, F110, FEBAN, FF_5, OB52, Trial Balance, F.01 |
| Configuration | OX02, OX18, OVX5, OVX6, OMS2, OMJJ, OBYC, VKOA, OT83 |

Items marked [VERIFY] or [DECISION] and highlighted placeholders must be confirmed for your release and project before baselining.